## Project Plan and Gantt
PROJECT PLAN AND GANTT CHART TEMPLATE
PROJECT NAME	PROJECT MANAGER	START DATE	END DATE		OVERALL PROGRESS		PROJECT DELIVERABLE
MeroBuilder	MICKUNAS Paulius	17-sept.	24-déc.		2 %
					SCOPE STATEMENT

TASKS	RESPONSIBLE	START	END	DAYS	STATUS
Conception du projet et des ides		9/17	10/1	14	Complete
Rapport et pseudo code		10/1	10/8	7	Complete
Fonction ligne		10/8	11/15	38	Complete
Fonction Point-Secteur : dispersion globale				0	Overdue
Fonction gestion du budget				0	In Progress
Fonction ligne globale		10/8	10/22	14	Overdue
Fonction ligne locale		10/22	11/7	16	Not Started
Fonction ligne contrôle		11/7	11/25	18	Not Started
Fonction Point-Secteur : dispersion locale				0	Not Started
Fonction Point-Secteur : dispersion globale				0	Not Started
Fonction construction possible				0	Not Started
				0	Not Started
				0	Not Started
				0	Not Started
LAUNCH		9/17	12/24	98

## Project Plan and Gantt - BLANK
PROJECT PLAN AND GANTT CHART TEMPLATE
PROJECT NAME	PROJECT MANAGER	START DATE	END DATE		OVERALL PROGRESS		PROJECT DELIVERABLE

					SCOPE STATEMENT

					Right click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.
TASKS	RESPONSIBLE	START	END	DAYS	STATUS
				0	Complete
				0	Complete
				0	Complete
				0	Overdue
				0	In progress
				0	In progress
				0	Not started
				0	Not started
				0	Not started
				0	Not started
				0	Not started
				0	Not started
				0	Not started
				0	Not started
				0	Not started
				0	Not started
				0	Not started
				0	Not started
				0	Not started
				0	Not started
				0	Not started
				0

## Stakeholder List
STAKEHOLDER LIST
NAME	POSITION	ROLE IN PROJECT	EMAIL ADDRESS	REQUIREMENTS	EXPECTATIONS
John Smith	VP of Product	Final approval of milestones	john@123.com	Downtime of no longer than 20 minutes	QA to take less than 1 week, marketing to promote new features in newsletter

## Cost Baseline
COST BASELINE
ITEM / TASK	% COMPLETE	BASE COST	COST	ACTUAL COST	% BUDGET SPENT
Extra devices for QA testing	50 %	$2 800	$3 500	$3 600	15 %

## Communication Plan
COMMUNICATION PLAN
COMMUNICATION TYPE	DELIVERABLE	DESCRIPTION	DELIVERY METHOD	FREQUENCY	OWNER	AUDIENCE
Presentation	15-minute PowerPoint presentation	Presentation to marketing team about new features	In-person	One time	Alex B.	Marketing team
Meetings	Standup meetings	Check in about status	In-person	2x a week	John S.	Project team

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.